Store Triage/Continuous Improvement Program Framework

- Store Selection & Prioritization: Identify stores based on performance metrics, operational challenges, and improvement opportunities

Pre-Event Preparation (2-3 weeks before)

- Data Analysis Package: Compile sales trends, donation volumes, inventory turnover, labor costs, and customer feedback for target store (Use RD Checklist, DGR Reporting – DGR Model, Production Report, Productivity Analysis Report, Sell Thru, PPI, Staff Schedule	)

- Store Walk-through and checklist: Conduct comprehensive assessment of sales floor, production area, donation door, backroom, and facility conditions

- Stakeholder Alignment: Schedule kickoff call with District Manager and Director of Retail to review objectives and priorities

- Team Assembly: Confirm participants including store management, key associates, and cross-functional support (merchandising, maintenance, etc.)

  - Action Plan Development: Create detailed improvement plans with owners, timelines, and success measures

  - DM Participation Required through duration of event

  - Retail director must be present as schedule allows and participate a minimum of 1 day

- Pre-event Survey: Collect input from store staff on pain points, obstacles, and improvement ideas

- Staff Interviews: One-on-one discussions with team members to understand challenges and gather insights

- Operations Review: Analyze workflows for receiving, sorting, pricing, merchandising, and rotation

Day 1: Assessment, Discovery, and Planning

- Opening Meeting: Review event goals, timeline, expectations, and success metrics with full team

- Quick Wins Identification: Highlight immediate improvements that can be implemented during the event

- Day 1 Debrief: Team huddle to share observations and align on priorities for Day 2

- Gap Analysis: Compare current state vs. best practices and company standards

- Root Cause Analysis: Identify underlying issues contributing to performance challenges

- Opportunity Brainstorm: Facilitated session to generate improvement ideas across all operational areas

- Priority Matrix: Rank opportunities by impact and feasibility to create action roadmap

- Resource Assessment: Identify budget, equipment, staffing, or training needs to support improvements

Day 2 (and day 3 if 4 day event): Implementation & Execution

- Morning Rally: Energize team and review day's objectives and assignments

- Begin Implementation: Start executing quick wins and high-priority actions

- Hands-on Improvements: Active implementation of planned changes (merchandising resets, workflow redesigns, signage updates, etc.)

- Visual Management: Install performance boards, workflow guides, or other visual tools

- Store Manager Coaching: One-on-one development session focused on leadership and operational excellence

- Workflow Training: Skill-building mini sessions for store team on new processes or best practices

- Progress Tracking: Monitor completion of action items and adjust plan as needed

- Afternoon Review: Assess progress and finalize plans for Day 4 (if applicable)

Day 3 (Day 4 if 4-day event): Finalization & Sustainability

- Complete Implementation: Finish remaining priority actions and improvements

- Store Team Training: Comprehensive walk-through of all changes with full staff

- Accountability Framework: Establish follow-up schedule, check-ins, and performance monitoring

- Compile debrief summary: notes/documents to share with leadership.

- Knowledge Capture: Document lessons learned, replicable solutions, and best practices

- Recognition & Celebration: Acknowledge team efforts and early wins

- Future Forward Roadmap: Outline continued improvement activities and milestones beyond the event in collaboration with DM/Director

- Closing Meeting: Review accomplishments, next steps, and commitment to ongoing excellence

Post-Event Follow-up

- Week 1 Check-in: Update with Store Manager and District Manager to address questions and sustain momentum

- Week 3: Assess progress on action items, review performance data, and provide additional support

- Best Practice Sharing: Communicate successful strategies to other stores through district meetings or internal communications

- Program Refinement: Incorporate lessons learned into future triage events

- Post event survey: 5-6 Questions

  - Was the event engaging?

  - Do you feel the facilitator communicated effectively?

  - Did the changes set the store up for success?

  - Did you learn something new?

  - Did you feel comfortable sharing your ideas?

  - Would you appreciate a return visit?

Key Success Factors

- Clear Ownership: Every action item has a designated owner and deadline

- Measurable Outcomes: Define specific, quantifiable goals (e.g., reduce backroom inventory by 30%, increase transaction size by 15%)

- Staff Engagement: Involve store associates in problem-solving and give them voice in solutions

- Balance Quick Wins & Long-term: Address immediate issues while building sustainable improvements

- Adaptability: Remain flexible to adjust plans based on discoveries during the event

- Resource Commitment: Ensure necessary support (budget, tools, people) to implement changes

- Leadership Alignment: Maintain consistent messaging and support from District Manager and Director of Retail throughout process